## Sheet1
Milestones | Day | Dynamic Motion | Start | Duration | MediaPro | Start | Duration | Ocubo | Start | Duration
DB Order | 2025-12-06 | Zone 1 Substructure | 2025-12-11 | 2 | Zone 1 1st Fix (High) | 2025-12-04 | 3
DM On Site | 2025-12-11 | Zone 2 Substructure | 2025-12-11 | 2 | Zone 2 1st Fix (High) | 2025-12-04 | 3
Work At hight Finished | 2025-12-11 | Zone 3 Substructure | 2025-12-11 | 2 | Zone 3 1st Fix (High) | 2025-12-04 | 4
SOFT OPENING! | 2025-12-20 | Zone 4 Substructure DONE |  |  | Zone 4 1st Fix (High) | 2025-12-04 | 5
|  | Zone 1 Gypsum | 2025-12-13 | 2 | Tray Painting All Zones | 2025-12-06 | 3
|  | Zone 2 Gypsum | 2025-12-13 | 2
|  | Zone 3 Gypsum | 2025-12-13 | 2 | All Zones 2nd Fix (High) | 2025-12-09 | 3
Zone 4 Gypsum DONE
[5 empty] | Zone 1 AVL Install | 2025-12-11 | 1
|  | Zone 1 Painting | 2025-12-14 | 1 | Zone 2 AVL Install | 2025-12-12 | 1
|  | Zone 2 Painting | 2025-12-14 | 1 | Zone 3 AVL Install | 2025-12-13 | 1
|  | Zone 3 Painting | 2025-12-14 | 1 | Zone 4 AVL Install | 2025-12-10 | 1
|  | Zone 4 Painting | 2025-12-11 | 1
[5 empty] | DB Install & Termination Zone 1/2 | 2025-12-10 | 2
|  | Zone 1 Vinyl Install | 2025-12-15 | 1 | DB Install & Termination Zone 3/4 | 2025-12-12 | 2
|  | Zone 2 Vinyl Install | 2025-12-15 | 1
|  | Zone 3 Vinyl Install | 2025-12-15 | 1 | All Zones LL 1st Fix | 2025-12-11 | 3
|  | Zone 4 Vinyl Install | 2025-12-12 | 1 | All Zones LL 2st Fix | 2025-12-12 | 3
[5 empty] | All Zones LL 3rd Fix | 2025-12-13 | 3
|  | Zone 1 Styro Install | 2025-12-15 | 3
|  | Zone 2 Styro Install | 2025-12-18 | 3 | Programming | 2025-12-16 | 5
|  | Zone 3 Styro Install | 2025-12-21 | 3
|  | Zone 4 Styro Install | 2025-12-13 | 3
|  | Zone 1 Prop Install | 2025-12-16 | 2
|  | Zone 2 Prop Install | 2025-12-19 | 2
|  | Zone 3 Prop Install | 2025-12-22 | 2
|  | Zone 4 Prop Install | 2025-12-14 | 2
|  | Fixings Pre-Install (RTN) | 2025-12-14 | 1
|  | Immersive Room ShowTex | 2025-12-13 | 4
Formulas:
Start = [Start, row above]+1
Start = [Start, row above]+[Duration, row above]

## Sheet2
| 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20
Foreman | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 4 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 3
Structure & Metal | 2025-12-11: 20; 2025-12-12: 20; 2025-12-13: 20; 2025-12-14: 20; 2025-12-15: 6; 2025-12-16: 6; 2025-12-17: 6; 2025-12-18: 6; 2025-12-19: 6; 2025-12-20: 6
Gypsum Board/Plaster | 2025-12-12: 15; 2025-12-13: 15; 2025-12-14: 15
Painting | 2025-12-11: 5; 2025-12-12: 5; 2025-12-13: 5; 2025-12-14: 5; 2025-12-15: 5; 2025-12-16: 5
Vinyl | 2025-12-12: 6; 2025-12-13: 6; 2025-12-14: 12; 2025-12-15: 12; 2025-12-16: 12
Styro Installers | 2025-12-13: 6; 2025-12-14: 6; 2025-12-15: 6; 2025-12-16: 6; 2025-12-17: 6; 2025-12-18: 6; 2025-12-19: 6
Fabrication Laborer | bar: 2025-12-14 to 2025-12-18
F&F Laborer | 2025-12-14: 6; 2025-12-15: 6; 2025-12-16: 6; 2025-12-17: 6; 2025-12-18: 6; 2025-12-19: 6; 2025-12-20: 6